## Sheet1
Name of Center WEST AFRICAN CENTRE FOR WATER, IRRIGATION AND SUSTAINABLE AGRICULTURE
Institution UNIVERSITY FOR DEVELOPMENT STUDIES |  |  |  | On Schedule
Country GHANA
Center Leader PROFESSOR FELIX K. ABAGALE |  |  |  | Behind Schedule
Annual Workplan (JANUARY-DECEMBER, 2022)
Work Plan Activities | Description | Partner Contribution (if relevant) | 2022 Y4Q1 |  |  | 2022 Y4Q2 |  |  | 2022 Y4Q3 |  |  | 2022 Y4Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1/ DLI 1: Institutional Readiness
Sub-Action 1a: Basic Readiness
Activity 1: IP; Procurement/Financial Manuals | [16 empty] | 0 | 0
Activity 2: Team Designation | [16 empty] | 0 | 0
Sub-Action 1b: Full Readiness
Activity 1: PM Certificate; Website; | [16 empty] | 0 | 0
Activity 2: Student Handbook with Scholarship Policy; Sectoral Advisory Board | [16 empty] | 0 | 0
SUB-TOTAL | [16 empty] | 0 | 0
Action 2/DLI 2: Independent external evaluation of development impact
Sub-Action 2a:
Activity 1: Implement recommendations of MTR | [16 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 2: Prepare for Second Development Impact Assessment | [16 empty] | 60000 | 100000 |  | Centre Leader/Deputy
SUB-TOTAL | [16 empty] | 60000 | 100000
Action 3/DLI 3: Student Recruitments and Enrollments
Sub-Action 3a: PhD Students
Activity 1: Recruit and enrol national and regional students to undertake PhD programmes | [16 empty] | 115000 | 145537 |  | Centre Leader/Deputy
Activity 2: Recruit and enrol national and regional students to undertake Masters programmes | [16 empty] | 70000 | 96767 |  | Centre Leader/Deputy
Activity 3: Financial support for PhD and Masters theses research | [16 empty] | 80000 | 0 |  | Centre Leader/Deputy
Activity 4: Recruit and enrol national and regional mid-career professionals to participate in professional short courses | [16 empty] | 30000 | 54012 |  | Centre Leader/Deputy
SUB-TOTAL | [16 empty] | 295000 | 296316
Action 4/DLI 4: Quality of Education
Sub-Action 4a:
Activity 1: Promoting quality assurances through self evaluation and gap assessment to ensure programmes meet international standards | [16 empty] | 0 | 202536 |  | Centre Leader/Deputy
Activity 2: Accreditation of designed PhD and Masters programmes by National Accreditation authorities (NAB/NCTE) and International Accreditation authorities | [16 empty] | 4000 | 202536 |  | Centre Leader/Deputy
Activity 3: Engagement of international faculty for teaching courses and workshops and cosupervision of students | [16 empty] | 45000 |  |  | Centre Leader/Deputy
Activity 4: Faculty exchange programmes with regional institutions | [16 empty] | 45000 |  |  | Centre Leader/Deputy
Activity 5: Students’ exchange programmes with national and regional institutions | [16 empty] | 35000 |  |  | Centre Leader/Deputy
Activity 6: Upgrade ICT infrastructure for research and learning | [16 empty] | 40000 |  |  | Centre Leader/Deputy
Activity 7: Set-up e-learning platforms and acquire elearning resources | [16 empty] | 30000 |  |  | Centre Leader/Deputy
Activity 8: Publication of at least 14 journal articles in indexed journals in Year 3 | [16 empty] | 65000 | 162030 |  | Centre Leader/Deputy
Activity 9: Obtain architectural drawings for office complex and secure approval | [16 empty] | 20000 |  |  | Centre Leader/Deputy
Activity 10: Construction of Centre Office Complex | [16 empty] | 0 | 303810 |  | Centre Leader/Deputy
SUB-TOTAL | [16 empty] | 284000 | 870912
Action 5/DLI 5: Relevance of Education & Research
Sub-Action 5a: Relevance of Education & Research
Activity 1: Identification and development of core sites for research and training | [16 empty] | 0 |  |  | Centre Leader/Deputy
Activity 2: Procurement of research and training equipment for core sites e.g. drip irrigation kits, GIS laboratory equipment, green house equipment, drones etc | [16 empty] | 160000 |  |  | Centre Leader/Deputy
Activity 3: Recruit two (2) fulltime laboratory technicians (12 months) | [16 empty] | 24800 |  |  | Centre Leader/Deputy
Activity 4: Recruit two (2) fulltime field technicians (12 months) | [16 empty] | 24800 |  |  | Centre Leader/Deputy
Activity 5: Procure one (1) cross country vehicle and one (1) 30-seater bus | [16 empty] | 0 |  |  | Centre Leader/Deputy
Activity 6: Capacity building in grantsmanship for Faculty and students | [16 empty] | 20000 |  |  | Centre Leader/Deputy
Activity 7: Writeshops for Centre students | [16 empty] | 10000 |  |  | Centre Leader/Deputy
Activity 8: Research by Centre staff, and in collaboration with national and regional partners | [16 empty] | 40000 |  |  | Centre Leader/Deputy
Activity 9: Sub-Action 5i: Conferences, symposia, seminars (including student-led conferences) on relevant topics (e.g. water management, irrigation, gender, sustainable agriculture, environment and ecosystems etc.) | [16 empty] | 30000 |  |  | Centre Leader/Deputy
Activity 10: Centre students and/or faculty undertake 1-3 months internship/attachment in relevant national and regional institutions (e.g. GIDA, 2iE etc) | [16 empty] | 60000 | 3549 |  | Centre Leader/Deputy
SUB-TOTAL | [16 empty] | 369600 | 0
Action 6/DLI 6: Timeliness and Quality of Fiduciary Management
Sub-Action 6a: Fiduciary Enhancement
Activity 1: Recruitment of Administrative Officer | [16 empty] | 12400 |  |  | Centre Leader/Deputy
Activity 2: Grants Coordinator | [16 empty] | 12400 |  |  | Centre Leader/Deputy
Activity 3: Recruitment of Accounts Officer | [16 empty] | 18600 |  |  | Centre Leader/Deputy
Activity 4: Equipment and office supplies for administrative team | [16 empty] | 0 |  |  | Centre Leader/Deputy
SUB-TOTAL | [16 empty] | 43400 | 0
Action/DLI 7: Institutional impact
Sub-Action 7a: Institutional impact
Activity 1: Development of a UDS national and regional outreach strategy | [16 empty] | 0 | 101268 |  | Centre Leader/Deputy
Activity 2: Strengthen regional partnerships and publicize Centre activities through outreach programmes (Branding and Communication) | [16 empty] | 30000 | 202535 |  | Centre Leader/Deputy
Activity 3: Support UDS Business and Innovations Incubation Centre to nurture entrepreneurial innovations by faculty and students (Entrepreneurship) | [16 empty] | 10000 | 25317 |  | Centre Leader/Director of BIIC
Activity 4: Develop University-wide research support services jointly with IIRaCS and support IIRaCS to attract grants and consultancies | [16 empty] | 16500 | 202535 |  | Centre Leader/Director of IIR
Activity 5: Logistics for the involvement of national stakeholders to improve the current merit-based selection process of UDS Vice Chancellor | [16 empty] | 0 |  |  | Centre Leader/Vice Chancellor
Activity 6: Improvement of meritbased selection criteria of UDS Deans and Heads of Department and development of guidelines for performance (Review of selection guidelines) | [16 empty] | 0 |  |  | Centre Leader/Vice Chancellor
Activity 7: Undertake self-evaluation and gap assessment of study programs to meet international accreditation standards | [16 empty] | 0 |  |  | Centre Leader/Director of DIRA
SUB-TOTAL | [16 empty] | 56500 | 531655
Action 8: Communication
Activity 1: Branding, Communications and Public Engagement Manager/Communication Officer | [16 empty] | 18600 |  |  | Centre Leader/Deputy
Activity 2: Recruitment of a ICT Manager | [16 empty] | 12400 |  |  | Centre Leader/Deputy
Activity 3: Recruitment of an ICT Technician | [16 empty] | 5000 |  |  | Centre Leader/Deputy
SUB-TOTAL | [16 empty] | 36000
GRAND-TOTAL | [16 empty] | 1144500
Note on V6: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus