## Sheet1
Name of Center WEST AFRICAN CENTRE FOR WATER, IRRIGATION AND SUSTAINABLE AGRICULTURE
Institution UNIVERSITY FOR DEVELOPMENT STUDIES |  |  |  | On Schedule
Country GHANA
Center Leader PROFESSOR FELIX K. ABAGALE |  |  |  | Behind Schedule
Annual Workplan (JANUARY-DECEMBER, 2023)
Work Plan Activities | Description | Partner Contribution (if relevant) | 2023 Y4Q1 |  |  | 2023 Y4Q2 |  |  | 2023 Y4Q3 |  |  | 2023 Y4Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1/ DLI 1: Institutional Readiness
Sub-Action 1a: Basic Readiness
Activity 1: IP; Procurement/Financial Manuals | [16 empty] | 0 | 0
Activity 2: Team Designation | [16 empty] | 0 | 0
Sub-Action 1b: Full Readiness
Activity 1: PM Certificate; Website; | [16 empty] | 0 | 0
Activity 2: Student Handbook with Scholarship Policy; Sectoral Advisory Board | [16 empty] | 0 | 0
SUB-TOTAL | [16 empty] | 0 | 0
Action 2/DLI 2: Independent external evaluation of development impact
Sub-Action 2a:
Activity 1: Implement recommendations of MTR | [16 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 2: Prepare for Second Development Impact Assessment | [16 empty] | 60000 | 121521 |  | Centre Leader/Deputy
SUB-TOTAL | [16 empty] | 60000 | 121521
Action 3/DLI 3: Student Recruitments and Enrollments
Sub-Action 3a: PhD Students
Activity 1: Recruit and enrol national and regional students to undertake PhD programmes | 17 | [13 empty] | 17 |  | 140000 | 101316 |  | Centre Leader/Deputy
Activity 2: Recruit and enrol national and regional students to undertake Masters programmes | 27 | [13 empty] | 27 |  | 80000 | 62308 |  | Centre Leader/Deputy
Activity 3: Financial support for PhD and Masters theses research | 91 | [13 empty] | 91 |  | 75000 | 0 |  | Centre Leader/Deputy
Activity 4: Recruit and enrol national and regional mid-career professionals to participate in professional short courses | 95 | [13 empty] | 95 |  | 25000 | 3422 |  | Centre Leader/Deputy
SUB-TOTAL | [16 empty] | 320000 | 167046
Action 4/DLI 4: Quality of Education
Sub-Action 4a:
Activity 1: Promoting quality assurances through self evaluation and gap assessment to ensure programmes meet international standards (to be completed by October 2023) | [16 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 2: Accreditation of designed PhD and Masters programmes by National Accreditation authorities (NAB/NCTE) and International Accreditation by AQAS | [16 empty] | 4000 | 405124.4085 |  | Centre Leader/Deputy
Activity 3: Engagement of international faculty for teaching courses and workshops and cosupervision of students | [16 empty] | 0 |  |  | Centre Leader/Deputy
Activity 4: Faculty exchange programmes with regional institutions | [16 empty] | 55000 |  |  | Centre Leader/Deputy
Activity 5: Students’ exchange programmes with national and regional institutions | [16 empty] | 42000 |  |  | Centre Leader/Deputy
Activity 6: Upgrade ICT infrastructure for research and learning | [16 empty] | 35000 |  |  | Centre Leader/Deputy
Activity 7: Set-up e-learning platforms and acquire elearning resources | [16 empty] | 40000 |  |  | Centre Leader/Deputy
Activity 8: Publication of at least 14 journal articles in indexed journals in Year 5 | [16 empty] | 55000 | 187399.0563 |  | Centre Leader/Deputy
Activity 9: Obtain architectural drawings for office complex and secure approval | [16 empty] | 0 |  |  | Completed
Activity 10: Construction of Centre Office Complex (Commissioning of completed building) | [16 empty] | 38000 | 303850 |  | Centre Leader/Deputy
SUB-TOTAL | [16 empty] | 269000 | 896373.4648
Action 5/DLI 5: Relevance of Education & Research
Sub-Action 5a: Relevance of Education & Research
Activity 1: Identification and development of core sites for research and training | [16 empty] | 0 |  |  | Centre Leader/Deputy
Activity 2: Procurement of research and training equipment for core sites e.g. drip irrigation kits, GIS laboratory equipment, green house equipment, drones etc | [16 empty] | 140300 |  |  | Centre Leader/Deputy
Activity 3: Salaries of two (2) fulltime laboratory technicians (12 months) | [16 empty] | 25200 |  |  | Centre Leader/Deputy
Activity 4: Salaries of two (2) fulltime field technicians (12 months) | [16 empty] | 25200 |  |  | Centre Leader/Deputy
Activity 5: Procure one (1) cross country vehicle and one (1) 30-seater bus | [16 empty] | 0 |  |  | Completed
Activity 6: Capacity building in grantsmanship for Faculty and students | [16 empty] | 20000 |  |  | Centre Leader/Deputy
Activity 7: Writeshops for Centre students for manuscript development | [16 empty] | 10000 |  |  | Centre Leader/Deputy
Activity 8: Research by Centre staff, and in collaboration with national and regional partners | [16 empty] | 40000 |  |  | Centre Leader/Deputy
Activity 9: Conferences, symposia, seminars (including student-led conferences) on relevant topics (e.g. water management, irrigation, gender, sustainable agriculture, environment and ecosystems etc.) | [16 empty] | 30000 |  |  | Centre Leader/Research and Grants Coordinator
Activity 10: Centre students and/or faculty undertake 1-3 months internship/attachment in relevant national and regional institutions (e.g. GIDA, 2iE etc) | [16 empty] | 50000 | 125685 |  | Centre Leader/Deputy
Activity 11: Support UDS Business Directorate to nurture entrepreneurial innovations by faculty and students (Entrepreneurship) | [16 empty] | 30000 | 102637 |  | Centre Leader/Director of BIIC
SUB-TOTAL | [16 empty] | 370700 | 228322
Action 6/DLI 6: Timeliness and Quality of Fiduciary Management
Sub-Action 6a: Fiduciary Enhancement
Activity 1:Salaries of Administrative Officer | [16 empty] | 12600 | 89127 |  | Centre Leader/Deputy
Activity 2: Grants Coordinator to facilitate grantsmanship and resource mobilsations through grants | [16 empty] | 12600 | 66845 |  | Centre Leader/Deputy
Activity 3: Salaries of Accounts Officer | [16 empty] | 18900 | 100268 |  | Centre Leader/Deputy
Activity 4: Equipment and office supplies for administrative team | [16 empty] | 0 | 111408 |  | Centre Leader/Deputy
Activity 5: ACE Impact Regional Workshops | [16 empty] | 50000 | 0 |  | Centre Leader/Deputy
SUB-TOTAL | [16 empty] | 94100 | 367648
Action/DLI 7: Institutional impact
Sub-Action 7a: Institutional impact
Activity 1: Development of a UDS national and regional outreach strategy | [16 empty] | 10000 | 101268 |  | Centre Leader/Deputy
Activity 2: Strengthen regional partnerships and publicize Centre activities through outreach programmes (Branding and Communication) | [16 empty] | 10000 | 202535 |  | Centre Leader/Deputy
Activity 3: Develop University-wide research support services jointly with IIR and support IIR to attract grants and consultancies | [16 empty] | 20000 | 202535 |  | Centre Leader/Director of IIR
Activity 4: Logistics for the involvement of national stakeholders to improve the current merit-based selection process of UDS Vice Chancellor | [16 empty] | 0 | 151901 |  | Centre Leader/Vice Chancellor
Activity 5: Improvement of merit based selection criteria of UDS Deans and Heads of Department and development of guidelines for performance (Review of selection guidelines) | [16 empty] | 5000 |  |  | Centre Leader/Vice Chancellor
Activity 6: Undertake self-evaluation and gap assessment of study programmes to meet international accreditation standards by AQAS | [16 empty] | 90000 | 25314 |  | Centre Leader/Director of DIRA
SUB-TOTAL | [16 empty] | 135000 | 683553
Action 8: Communication
Activity 1: Salaries of Branding, Communications and Public Engagement Manager/Communication Officer | [16 empty] | 18900 |  |  | Centre Leader/Deputy
Activity 2: Salaries of an ICT Manager | [16 empty] | 12600 |  |  | Centre Leader/Deputy
Activity 3: Salaries of an ICT Technician | [16 empty] | 5000 |  |  | Centre Leader/Deputy
SUB-TOTAL | [16 empty] | 36500
GRAND-TOTAL | [16 empty] | 1285300 | 2464463.4648
Note on V6: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus
Note on A19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there an activity on The assessment itself? It seems to me that the preparation is taking too much time
Note on A45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Why is this process of recruitment taking too much time>