## Sheet1
Name of Center WEST AFRICAN CENTRE FOR WATER, IRRIGATION AND SUSTAINABLE AGRICULTURE
Institution UNIVERSITY FOR DEVELOPMENT STUDIES |  |  |  | On Schedule
Country GHANA
Center Leader PROFESSOR FELIX K. ABAGALE |  |  |  | Behind Schedule
Annual Workplan (JANUARY-DECEMBER, 2024)
Work Plan Activities | Description | Partner Contribution (if relevant) | 2024 Y4Q1 |  |  | 2024 Y4Q2 |  |  | 2024 Y4Q3 |  |  | 2024 Y4Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1/ DLI 1: Institutional Readiness
Sub-Action 1a: Basic Readiness
Activity 1: IP; Procurement/Financial Manuals | Procurment and Financial manuals developed in use and available online on Centres website | [15 empty] | 0 | 0
Activity 2: Team Designation | Team in place with appropriate designations and appointment letters | [15 empty] | 0 | 0
Sub-Action 1b: Full Readiness
Activity 1: PM Certificate; Website; | Certificate and website in place and active | [15 empty] | 0 | 0
Activity 2: Student Handbook with Scholarship Policy; Sectoral Advisory Board | Student handbook is completed and available online on the Centre's website and all Boards in place and functioing | [15 empty] | 0 | 0
SUB-TOTAL | [16 empty] | 0 | 0
Action 2/DLI 2: Independent external evaluation of development impact
Sub-Action 2a:
Activity 1: Implement recommendations of MTR | Recommendations of MTR are being implemented | [15 empty] | 30000 | 121521 |  | Centre Leader/Deputy
Activity 2: Prepare for Second Development Impact Assessment | Preparations are in place for the assessment process for the second development imapct assessment | [15 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 3: Orientation on Gender Based Violence and Sexual harassment | WACWISA Fresh men and Women | [15 empty] | 10000 | 0 |  | Centrer Leader/Safeguards Officer
Activity 4: Sensitization on Gender Based Violence and Sexual harassment | University Community (Staff and Student) | [15 empty] | 10000 | 0 |  | Centrer Leader/Safeguards Officer
Activity 5: Sensitization on Environment and Safety | University Community (Staff and Student) | [15 empty] | 10000 | 0 |  | Centrer Leader/Safeguards Officer
Activity 6: Compliant Management: Establish a system to manage complaints boxes and register for sexual harassment related complaints, gender based violence | Center Staff and Students | [15 empty] | 8000 | 0 |  | Centrer Leader/Safeguards Officer
SUB-TOTAL | [16 empty] | 30000 | 121521
Action 3/DLI 3: Student Recruitments and Enrollments
Sub-Action 3a: PhD Students
Activity 1: Recruit and enrol national and regional students to undertake PhD programmes | Enrol 17 PhD students for the 2023/2024 academic year | [13 empty] | 2 |  | 20000 | 25956 |  | Centre Leader/Deputy
Activity 2: Recruit and enrol national and regional students to undertake Masters programmes | Enrol 27 Masters students for the 2023/2024 academic year | [13 empty] | 5 |  | 35000 | 53690 |  | Centre Leader/Deputy
Activity 3: Financial support for PhD and Masters theses research | Tuition and Research Support for 91 Masters and PhD students will be paid for the year | [13 empty] | 25 |  | 75000 | 0 |  | Centre Leader/Deputy
Activity 4: Recruit and enrol national and regional mid-career professionals to participate in professional short courses | Provide career oriented Professional Short Courses to 95 mid-career professionals for the year | [13 empty] | 50 |  | 7000 | 10000 |  | Centre Leader/Deputy
SUB-TOTAL | [16 empty] | 137000 | 89646
Action 4/DLI 4: Quality of Education
Sub-Action 4a:
Activity 1: Promoting quality assurances through self evaluation and gap assessment to ensure programmes meet international standards (to be completed by October 2023) | This has already been done and used for international programme accreditation | [15 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 2: Accreditation of designed PhD and Masters programmes by National Accreditation authorities (NAB/NCTE) and International Accreditation by AQAS | This activity has been completed and accrditation certificate received | [15 empty] | 4000 | 0 |  | Centre Leader/Deputy
Activity 3: Engagement of international faculty for teaching courses and workshops and cosupervision of students | Cosupervision of students have started and international faculty exchange will be done in 2024 | [15 empty] | 10000 | 0 |  | Centre Leader/Deputy
Activity 4: Faculty exchange programmes with regional institutions | Faculty exchange to support teaching and supervision with regional students will be done in 2024 to selected institutions | [15 empty] | 15000 | 0 |  | Centre Leader/Deputy
Activity 5: Students’ exchange programmes with national and regional institutions | Stduents exchange visits for periods ranging from 2 weeks to 3 months will be done and will involve local partners in Ghana and regional pertners | [15 empty] | 10000 | 0 |  | Centre Leader/Deputy
Activity 6: Upgrade ICT infrastructure for research and learning | The Centre has installed the needed infrastructure to support teaching and research and will continue to collaborate with the ICT Directorate to ensure and promote excellence. | [15 empty] | 10000 | 0 |  | Centre Leader/Deputy
Activity 7: Set-up e-learning platforms and acquire elearning resources | The last mile of fine tuning the available e-learning platforms will be done jointy with the ICT Directorate | [15 empty] | 10000 | 0 |  | Centre Leader/Deputy
Activity 8: Publication of at least 14 journal articles in indexed journals in Year 5 | Researchers in the Centre will continue to publish relevant findings in high ranked journal outlets | [15 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 9: Obtain architectural drawings for office complex and secure approval | This has been completed and building is under occupation | [15 empty] | 0 | 0 |  | Completed
Activity 10: Installation of Lift, commissioning and maintenance of Centre Office Complex | The Centre will work with the procurement Directorate to procure and install a lift, commission the office complex and carryout maintainance thereon | [15 empty] | 50000 | 303810 |  | Centre Leader/Deputy
SUB-TOTAL | [16 empty] | 109000 | 303810
Action 5/DLI 5: Relevance of Education & Research
Sub-Action 5a: Relevance of Education & Research
Activity 1: Continuous improvement and development of core sites for research and training | The Centre will continue to collaborate with partners to develop new sites (when need be) and maintain existing sites | [15 empty] | 6000 | 0 |  | Centre Leader/Deputy
Activity 2: Procurement and maintenance of research and training equipment for core sites e.g. drip irrigation kits, GIS laboratory equipment, green house equipment, drones etc | Procurement in this regard is almost complete and the last mile of the equipment will be installed and maintenance of the infrastructure will be done to ensure functionality | [15 empty] | 20000 | 0 |  | Centre Leader/Deputy
Activity 3: Salaries of two (2) fulltime laboratory technicians (12 months) | Laboratory staff engaged are being supported by the University interms of payment of salaries and they are being assisted by national service personnel | [15 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 4: Salaries of two (2) fulltime field technicians (12 months) | Salaries of 2 fulltime field technicians are being paid by the Centre and this will continue as such. | [15 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 5: Maintenance of the procured cross country vehicle and 30-seater bus | Regular and routine maintenance to ensure efficiency and longitivity of the lifespan of the vehicles will continue | [15 empty] | 12000 | 0 |  | Completed
Activity 6: Capacity building in grantsmanship for Faculty and students | Capacity building workshops for Faculty and Staff will continue for improved grantsmanship in the Centre and University | [15 empty] | 20000 | 0 |  | Centre Leader/Deputy
Activity 7: Writeshops for Centre students for manuscript development | At least three (3) writeshops will be organised for Centre students on manuscript development | [15 empty] | 15000 | 0 |  | Centre Leader/Deputy
Activity 8: Research by Centre staff, and in collaboration with national and regional partners | Support research activities of Centre staff to collaborate with partners both national and regionally | [15 empty] | 40000 | 0 |  | Centre Leader/Deputy
Activity 9: Conferences, symposia, seminars (including student-led conferences) on relevant topics (e.g. water management, irrigation, gender, sustainable agriculture, environment and ecosystems etc.) | The Centre will organise one (1) conference and two (2) seminars in 2024 and also will support students to organise student-led conference or seminars. | [15 empty] | 50000 | 0 |  | Centre Leader/Research and Grants Coordinator
Activity 10: Centre students and/or faculty undertake 1-3 months internship/attachment in relevant national and regional institutions (e.g. GIDA, 2iE etc) | There will be continued support to Centre students and staff to undetake intenships in national and regional institutions to support in building capacity and knowledge exchange | [15 empty] | 25000 | 83093 |  | Centre Leader/Deputy
Activity 11: Support School of Business to nurture entrepreneurial innovations by faculty and students (Entrepreneurship) | The School of Business shall be supported to nurture entrepreneurial innovations of students and faculty emanating from research works. | [15 empty] | 40000 | 101268 |  | Centre Leader/Director of BIIC
SUB-TOTAL | [16 empty] | 228000 | 184361
Action 6/DLI 6: Timeliness and Quality of Fiduciary Management
Sub-Action 6a: Fiduciary Enhancement
Activity 1: Allowances and fringe benefits of Administrative Officer | Support Project Administrative staff with relevant tools and incentives for the management of the Centre | [15 empty] | 12000 | 77799 |  | Centre Leader/Deputy
Activity 2: Internal audit committee meetings and operations | The Centre Management will continue to work with the Audit Directorate of the University as well as the Audit Committee to promote compliance in its operations | [15 empty] | 21000 | 62756 |  | Centre Leader/Deputy
Activity 3: Allowances and fringe benefits of Accounts Officer | Support Project Accounts Officer staff with relevant tools and incentives for the discharge of his work | [15 empty] | 12000 | 42425 |  | Centre Leader/Deputy
Activity 4: Equipment and office supplies for administrative team | Provide Project Administrative team with relevant tools, equipment and office supplies for improved performance | [15 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 5: ACE Impact Regional Workshops | Participate in ACE Impact regional workshops | [15 empty] | 50000 | 0 |  | Centre Leader/Deputy
SUB-TOTAL | [16 empty] | 95000 | 182980
Action/DLI 7: Institutional impact
Sub-Action 7a: Institutional impact
Activity 1: Development of a UDS national and regional outreach strategy towards institutional accreditation | The development of the necessary documentation for this will be completed in 2024 | [15 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 2: Strengthen regional partnerships and publicize Centre activities through outreach programmes (Branding and Communication) | Enhance branding and communication on the activities of the Centre through its partnerships and outreach programmes to improved visibility | [15 empty] | 10000 | 0 |  | Centre Leader/Deputy
Activity 3: Develop University-wide research support services jointly with IIR and support IIR to attract grants and consultancies for institutional impact | The collaboration with the Institute of Interdisciplinary Research (IIR) has been working since 2019 and strategies to enhance the working relationship especially to attract research grants and consultancies shall be explored within the period. | [15 empty] | 20000 | 101268 |  | Centre Leader/Director of IIR
Activity 4: Logistics for the involvement of national stakeholders to improve the current ICT infrastruture towards PASET Regional Benchmarking | Implementation in this regard will be enhanced as it has already started and this will lead to improved results relating to the PASET Regional Benchmarking | [15 empty] | 0 | 50634 |  | Centre Leader/Vice Chancellor
Activity 5: Improvement of merit based selection criteria of UDS Deans and Heads of Department | Merit-based selection processes of institutional management shall be supported by the Centre to promote transparency and fairness | [15 empty] | 0 | 0 |  | Centre Leader/Vice Chancellor
Activity 6: Undertake self-evaluation and gap assessment of study programmes to meet international accreditation standards by AQAS | This has completed and accreditation certificates received | [15 empty] | 0 | 278486 |  | Centre Leader/Director of DIRA
SUB-TOTAL | [16 empty] | 30000 | 430388
Action 8: Communication
Activity 1: Salaries of Branding, Communications and Public Engagement Manager/Communication Officer | Salaries of Branding and Communication Officer are being paid by the University and will continue for the year | [15 empty] | 0 |  |  | Centre Leader/Deputy
Activity 2: Salaries of an ICT Manager | Salaries of ICT Manager are being paid by University and will continue for the year | [15 empty] | 0 |  |  | Centre Leader/Deputy
Activity 3: Salaries of an ICT Technician | Salaries for ICT Technician are being paid by the University and will continue for the year | [15 empty] | 0 |  |  | Centre Leader/Deputy
SUB-TOTAL | [16 empty] | 0
GRAND-TOTAL | [16 empty] | 629000 | 1312706
Note on V6: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus
Note on A19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there an activity on The assessment itself? It seems to me that the preparation is taking too much time
Note on A49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Why is this process of recruitment taking too much time>