## Sheet1
Name of Center WEST AFRICAN CENTRE FOR WATER, IRRIGATION AND SUSTAINABLE AGRICULTURE
Institution UNIVERSITY FOR DEVELOPMENT STUDIES |  |  |  | On Schedule
Country GHANA
Center Leader PROFESSOR FELIX K. ABAGALE |  |  |  | Behind Schedule
Annual Workplan (JANUARY-JUNE, 2025)
Work Plan Activities | Description | Partner Contribution (if relevant) | 2025 Y5Q1 |  |  | 2025 Y5Q2 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun
Action 1/ DLI 1: Institutional Readiness
Sub-Action 1a: Basic Readiness
Activity 1: IP; Procurement/Financial Manuals | Procurment and Financial manuals developed in use and available online on Centres website | [9 empty] | 0 | 0
Activity 2: Team Designation | Team in place with appropriate designations and appointment letters | [9 empty] | 0 | 0
Sub-Action 1b: Full Readiness
Activity 1: PM Certificate; Website; | Certificate and website in place and active | [9 empty] | 0 | 0
Activity 2: Student Handbook with Scholarship Policy; Sectoral Advisory Board | Student handbook is completed and available online on the Centre's website and all Boards in place and functioing | [9 empty] | 0 | 0
SUB-TOTAL | [10 empty] | 0 | 0
Action 2/DLI 2: Independent external evaluation of development impact
Sub-Action 2a:
Activity 1: Implement recommendations of MTR | Recommendations of MTR are being implemented | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 2: Prepare for Second Development Impact Assessment | Preparations for the assessment process for the second development impAct assessment has been completed | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 3: Orientation on Gender Based Violence and Sexual harassment | WACWISA Fresh men and Women | [9 empty] | 0
Activity 4: Sensitization on Gender Based Violence and Sexual harassment | University Community (Staff and Students) | [9 empty] | 0
Activity 5: Sensitization on Environment and Safety | University Community (Staff and Students) | [9 empty] | 0
Activity 6: Compliant Management: Establish a system to manage complaints boxes and register for sexual harassment related complaints gender based violence | Center Staff and Students | [9 empty] | 0
SUB-TOTAL | [10 empty] | 0 | 0
Action 3/DLI 3: Student Recruitments and Enrollments
Sub-Action 3a: PhD Students
Activity 1: Recruit and enrol national and regional students to undertake PhD programmes | Enrolment of PhD students | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 2: Recruit and enrol national and regional students to undertake Masters programmes | Enrolment of Masters students | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 3: Financial support for PhD and Masters theses research | Tuition and Research Support for Masters and PhD students will be paid for the year | [9 empty] | 75000 | 0 |  | Centre Leader/Deputy
Activity 4: Recruit and enrol national and regional mid-career professionals to participate in professional short courses | Provide career oriented Professional Short Courses to mid-career professionals | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
SUB-TOTAL | [10 empty] | 75000 | 0
Action 4/DLI 4: Quality of Education
Sub-Action 4a:
Activity 1: Promoting quality assurances through self evaluation and gap assessment to ensure programmes meet international standards | This has already been done and used for international programme accreditation | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 2: Accreditation of designed PhD and Masters programmes by National Accreditation authorities (NAB/NCTE) and International Accreditation authorities | This activity has been completed and accrditation certificate received | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 3: Engagement of international faculty for teaching courses and workshops and cosupervision of students | Cosupervision of students have started and international faculty exchange will be continued in 2025 | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 4: Faculty exchange programmes with regional institutions | Faculty exchange to support teaching and supervision with regional students will continue in 2025 to selected institutions | [9 empty] | 30000 | 0 |  | Centre Leader/Deputy
Activity 5: Students’ exchange programmes with national and regional institutions | Students exchange visits for periods ranging from 2 weeks to 3 months will continue in 2025 and will involve local partners in Ghana and regional pertners | [9 empty] | 20000 | 0 |  | Centre Leader/Deputy
Activity 6: Upgrade ICT infrastructure for research and learning | The Centre has installed the needed infrastructure to support teaching and research and will continue to collaborate with the ICT Directorate to ensure and promote excellence. | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 7: Set-up e-learning platforms and acquire elearning resources | The last mile of fine tuning the available e-learning platforms will be done jointy with the ICT Directorate | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 8: Publication of at least 10 journal articles in indexed journals | Researchers in the Centre will continue to publish relevant findings in high ranked journal outlets | [9 empty] | 10000 | 0 |  | Centre Leader/Deputy
Activity 9: Obtain architectural drawings for office complex and secure approval | This has been completed and building is under occupation | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 10: Construction of Centre Office Complex | The Centre will work with the procurement Directorate to procure and install a lift and carryout maintainance thereon | [9 empty] | 150000 | 0 |  | Centre Leader/Deputy
SUB-TOTAL | [10 empty] | 210000 | 0
Action 5/DLI 5: Relevance of Education & Research
Sub-Action 5a: Relevance of Education & Research
Activity 1: Identification and development of core sites for research and training | The Centre will continue to collaborate with partners to develop new sites (when need be) and maintain existing sites | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 2: Procurement of research and training equipment for core sites e.g. drip irrigation kits, GIS laboratory equipment, green house equipment, drones etc | Maintenance of the infrastructure will be done to ensure functionality | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 3: Recruit two (2) fulltime laboratory technicians (12 months) | Laboratory staff engaged by the University | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 4: Recruit two (2) fulltime field technicians (12 months) | Salaries of 2 fulltime field technicians are being paid by the Centre and this will continue as such | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 5: Procure one (1) cross country vehicle and one (1) 30-seater bus | Regular and routine maintenance to ensure efficiency and longitivity of the lifespan of vehicles. | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 6: Capacity building in grantsmanship for Faculty and students | Capacity building workshops for Faculty and Staff will continue for improved grantsmanship in the Centre and University | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 7: Writeshops for Centre students for manuscript development | At least two (2) writeshops will be organised for Centre students on manuscript development | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 8: Research by Centre staff, and in collaboration with national and regional partners | Support research activities of Centre staff to collaborate with partners both national and regionally | [9 empty] | 15000 | 0 |  | Centre Leader/Deputy
Activity 9: Conferences, symposia, seminars (including student-led conferences) on relevant topics (e.g. water management, irrigation, gender, sustainable agriculture, environment and ecosystems etc.) | The Centre will organise two (2) seminars in 2025 and also will support students to organise student-led conference or seminars. | [9 empty] | 20000 | 0 |  | Centre Leader/Deputy
Activity 10: Centre students and/or faculty undertake 1-3 months internship/attachment in relevant national and regional institutions (e.g. GIDA, 2iE etc) | There will be continued support to Centre students and staff to undetake intenships in national and regional institutions to support in building capacity and knowledge exchange | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 11: Support Intellectual property Office to nurture entrepreneurial innovations by faculty and students (Entrepreneurship) | The Intellectual Property Office will be supported to nurture entrepreneurial innovations of students and faculty emanating from research works. | [9 empty] | 10000 | 0 |  | Centre Leader/Intellectutal Property Office
SUB-TOTAL | [10 empty] | 45000 | 0
Action 6/DLI 6: Timeliness and Quality of Fiduciary Management
Sub-Action 6a: Fiduciary Enhancement
Activity 1: Allowances and fringe benefits of Administrative Officer | Support Project Administrative staff with relevant tools and incentives for the management of the Centre | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 2: Internal audit committee meetings and operations | The Centre Management will continue to work with the Audit Directorate of the University as well as the Audit Committee to promote compliance in its operations | [9 empty] | 8000 | 0 |  | Centre Leader/Deputy
Activity 3: Allowances and fringe benefits of Accounts Officer | Support Project Accounts Officer staff with relevant tools and incentives for the discharge of his work | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 4: Equipment and office supplies for administrative team | Provide Project Administrative team with relevant tools, equipment and office supplies for improved performance | [9 empty] | 3000 | 0 |  | Centre Leader/Deputy
Activity 5: ACE Impact Regional Workshops | Participate in ACE Impact regional workshops | [9 empty] | 10000 | 0
SUB-TOTAL | [10 empty] | 21000 | 0
Action/DLI 7: Institutional impact
Sub-Action 7a: Institutional impact
Activity 1: Development of a UDS national and regional outreach strategy | This was completed in 2024 | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 2: Strengthen regional partnerships and publicize Centre activities through outreach programmes (Branding and Communication) | Enhance branding and communication on the activities of the Centre | [9 empty] | 5000 | 0 |  | Centre Leader/Deputy
Activity 3: Develop University-wide research support services jointly with IIR and support IIR to attract grants and consultancies | Continued collaboration with the Institute of Interdisciplinary Research (IIR) | [9 empty] | 5000 | 0 |  | Centre Leader/Director of IIR
Activity 4: Logistics for the involvement of national stakeholders to improve the current ICT infrastruture towards PASET Regional Benchmarking | Implementation in this regard will be enhanced as it has already started and this will lead to improved results relating to the PASET Regional Benchmarking | [9 empty] | 0 | 0 |  | Centre Leader/Vice Chancellor
Activity 5: Improvement of merit based selection criteria of UDS Deans and Heads of Department | Merit-based selection processes of institutional management shall be supported by the Centre to promote transparency and fairness | [9 empty] | 0 | 0 |  | Centre Leader/Vice Chancellor
Activity 6: Undertake self-evaluation and gap assessment of study programs to meet international accreditation standards | This has completed and accreditation certificates received | [9 empty] | 0 | 0 |  | Centre Leader/Director of DIRA
SUB-TOTAL | [10 empty] | 10000 | 0
Action 8: Communication
Activity 1: Salaries of Branding, Communications and Public Engagement Manager/Communication Officer | Salaries of Branding and Communication Officer are being paid by the University and will continue for the year | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 2: Salaries of an ICT Manager | Salaries of ICT Manager are being paid by University and will continue for the year | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
Activity 3: Salaries of an ICT Technician | Salaries for ICT Technician are being paid by the University and will continue for the year | [9 empty] | 0 | 0 |  | Centre Leader/Deputy
SUB-TOTAL | [10 empty] | 0 | 0
Others
ACE Regional Workshop @10 | Centre Team attend Regional Workshop | [9 empty] | 10000 | 0 |  | Centre Leader
Internal and External Audit Activities | Internal and External Auditors undertake final audit activities | [9 empty] | 15000 | 0 |  | Centre Leader
Undertake ESMP Audit Activities | Provide Adequate signages, etc | [9 empty] | 15000 | 0 |  | Centre Leader
Undertake ESMP Implementation Audit | Engage an ESMP Auditor | [9 empty] | 25000 | 0 |  | Centre Leader
Project Closing Report | Submit Project Closing Report to include, procurement, financial, & technical reports on the Centre | [9 empty] | 20000 | 0 |  | Centre Leader
GRAND-TOTAL | [10 empty] | 446000 | 0
Note on N6: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus