## Services
Procurement Entity
Budget Period
Source of Funding | [6 empty] | Preparation of Request for Proposals | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F) |  |  |  |  | Negotiations |  |  | Contract Finalization |  |  |  | Contract Implementation
Contract Packages* | Plan vs. Actual | Package Number | Estimated Amount (USD) | Selection Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Executing Agency | Invitation Date | Submission/ Opening Date | Complete Evaluation Report (T) | Opening Financial Proposals | Complete Eval Report (T) (F) | Approval of Eval Report (T) (F) | Plan vs. Actual | Negotiations | Submission Draft Contract | Approval of Negotiation report | Contract Amount (USD) | Contract ward | Contract Signature | Plan vs. Actual | Mobilization Advance Payment (USD) | Draft Report | Final Report | Final Cost (USD)
[6 empty] | Duration | [7 empty] | Duration | [6 empty] | Duration
EMSP Assessment/Audit | Plan | NR/UDS/WACWISA/CS/001/25 | 16666.67 | Quality Based Selection | ETC | Plan | 2025-02-23 | 2025-03-02 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | Plan | 2025-04-20 | 2025-04-27 | 2025-05-11 | 16666.67 | 2025-05-16 | 2025-05-23 | Plan | 1666.67 | 2025-06-17 | 2025-06-22 | 16666.67
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
2 | Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
3 | Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
4 | Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
5 | Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
6 | Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
7 | Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
8 | Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
9 | Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost | Plan |  | 16666.67 |  |  | Plan | [7 empty] | Plan |  |  |  | 16666.67 |  |  | Plan |  |  |  | 16666.67
| Actual |  | 0 |  |  | Actual | [7 empty] | Actual |  |  |  | 0 |  |  | Actual |  |  |  | 0
Fill gray cells only!
Formulas:
Negotiations = [Approval of Eval Report (T) (F)]+7
Submission Draft Contract = [Negotiations]+7
Approval of Negotiation report = [Submission Draft Contract]+14
Contract ward = [Approval of Negotiation report]+5
Contract Signature = [Contract ward]+7
Draft Report = [Contract Signature]+25
Final Report = [Draft Report]+5

## Goods
Procurement Entity: University for Development Studies
Budget Period: 01/01/2025-30/06/2025
Source of Funding: WACWISA-WORLD BANK |  |  | BASIC DATA |  |  |  | Tender Documents | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Goods Delivery
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (USD) | Procurement Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing-Opening | Submission Tender Eval Rpt | Aproval by Final Authority | Plan vs. Actual | Contract Amount (USD) | Date Contract Award | Date Contract Signature | Arrival of Goods | Final Acceptance | Final Cost USD
Procurement of Molecular Biology Liquid handling Sample preparation Kits | Plan | NR/UDS/WACWISA/GD/001/25 | 53313.26 | NCT | ETC | Plan | 2025-02-17 | 2025-02-22 | 2025-03-08 | 2025-03-15 | 2025-03-22 | Plan | 53313.26 | 2025-03-29 | 2025-04-05 | 2025-05-05 | 2025-05-10 | 53313.26
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Procurement of Various Micro Biology Laboratory Equipment | Plan | NR/UDS/WACWISA/GD/002/25 | 53150.38 | NCT | ETC | Plan | 2025-02-17 | 2025-02-22 | 2025-03-08 | 2025-03-15 | 2025-03-22 | Plan | 53150.38 | 2025-03-29 | 2025-04-05 | 2025-05-05 | 2025-05-10 | 53150.38
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Procurement of Laboratory Sample processing Equipment | Plan | NR/UDS/WACWISA/GD/003/25 | 50833.09 | NCT | ETC | Plan | 2025-02-17 | 2025-02-22 | 2025-03-08 | 2025-03-15 | 2025-03-29 | Plan | 50833.09 | 2025-04-05 | 2025-04-12 | 2025-05-12 | 2025-05-17 | 50833.09
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Laboratory Reagents | Plan | NR/UDS/WACWISA/GD/004/25 | 16666.67 | NCT | ETC | Plan | 2025-02-17 | 2025-02-22 | 2025-03-08 | 2025-03-15 | 2025-03-22 | Plan | 16666.67 | 2025-03-29 | 2025-04-05 | 2025-05-05 | 2025-05-12 | 16666.67
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Stationery | Plan | NR/UDS/WACWISA/GD/005/25 | 3446.67 | PQ | VC | Plan | 2025-01-13 | 2025-01-18 | 2025-02-01 | 2025-02-08 | 2025-02-15 | Plan | 3446.67 | 2025-02-22 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 3446.67
| Actual | NR/UDS/WACWISA/GD/005/25 | 3,191.67 | PQ | VC | Actual | 2025-01-16 | 2025-01-21 | 2025-01-28 | 2025-01-28 | 2025-02-06 | Plan | 3,191.67 | 2025-02-07 | 2025-02-14 | 2025-02-21 | 2025-02-28 | 3,191.67
Glassware and Consumables | Plan | NR/UDS/WACWISA/GD/006/25 | 16400 | NCT | ETC | Plan | 2025-02-17 | 2025-02-24 | 2025-03-10 | 2025-03-17 | 2025-03-24 | Plan | 16400 | 2025-03-31 | 2025-04-07 | 2025-05-07 | 2025-05-14 | 16400
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Communication items | Plan | NR/UDS/WACWISA/GD/007/25 | 6066.67 | PQ | VC | Plan | 2025-02-19 | 2025-02-24 | 2025-03-10 | 2025-03-17 | 2025-03-24 | Plan | 6066.67 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-05-14 | 6066.67
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Cleaning Materials | Plan | NR/UDS/WACWISA/GD/008/25 | 3400 | PQ | VC | Plan | 2025-02-19 | 2025-02-24 | 2025-03-10 | 2025-03-17 | 2025-03-24 | Plan | 3400 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 3400
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Toners and Cartridges | Plan | NR/UDS/WACWISA/GD/009/25 | 9350 | NCT | ETC | Plan | 2025-02-17 | 2025-02-22 | 2025-03-08 | 2025-03-15 | 2025-03-22 | Plan | 9350 | 2025-03-29 | 2025-04-05 | 2025-04-12 | 2025-04-26 | 9350
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Tyres and Batteries | Plan | NR/UDS/WACWISA/GD/010/25 | 6066.67 | PQ | VC | Plan | 2025-02-19 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | Plan | 6066.67 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 6066.67
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Procurement of Molecular Biology Sample Preparation Equipment | Plan | NR/UDS/WACWISA/GD/011/25 | 53289.85 | NCT | ETC | Plan | 2025-02-25 | 2025-03-02 | 2025-03-16 | 2025-03-23 | 2025-03-30 | Plan | 53289.85 | 2025-04-06 | 2025-04-13 | 2025-05-13 | 2025-06-02 | 53289.85
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Procurement of Gasses and Water Purification System Consumables | Plan | NR/UDS/WACWISA/GD/012/25 | 42436.39 | NCT | ETC | Plan | 2025-02-25 | 2025-03-02 | 2025-03-16 | 2025-03-23 | 2025-03-30 | Plan | 42436.39 | 2025-04-06 | 2025-04-13 | 2025-05-13 | 2025-06-02 | 42436.39
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Supply of Deutrium Lam for AAS System | Plan | NR/UDS/WACWISA/GD/013/25 | 4700 | PQ | VC | Plan | 2025-02-25 | 2025-03-04 | 2025-03-18 | 2025-03-25 | 2025-04-01 | Plan | 4700 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 29/04/2025 | 4700
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Procurement of Multi-Q ultra Pure water Purification System | Plan | NR/UDS/WACWISA/GD/014/25 | 48316.98 | NCT | ETC | Plan | 2025-02-25 | 2025-03-04 | 2025-03-18 | 2025-03-25 | 2025-04-01 | Plan | 48316.98 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 29/04/2025 | 48316.98
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Total Cost | Plan |  | 367436.63 |  |  | Plan | [5 empty] | Plan | 367436.63 |  |  |  |  | 367436.63
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Formulas:
Tendering Period = [Tender Documents]+5
Tender Closing-Opening = [Tendering Period]+14
Tender Evaluation = [Tender Closing-Opening]+7
Aproval by Final Authority = [Tender Evaluation]+7
Date Contract Award = [Aproval by Final Authority]+7
Date Contract Signature = [Date Contract Award]+7
Goods Delivery = [Date Contract Signature]+30
Final Acceptance = [Goods Delivery]+5

## Works
Procurement Entity:University for Development Studies
Budget Period:01/01/2025 - 30/06/2025
Source of Funding: IGF & GETFUND |  |  | BASIC DATA |  |  |  |  | Tender Documents | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (USD) | Procurement Method | Pre-or Post Qualification | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing-Opening | Submission Tender Eval Rpt | Aproval by Final Authority | Plan vs. Actual | Contract Amount (USD) | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost (USD)
Pavement works for Car Par | Plan | NR/UDS/WACWISA/WK/001/25 | 10000 | PQ | POST | HE | Plan | 2025-02-17 | 2025-02-22 | 2025-03-08 | 2025-03-15 | 2025-03-22 | Plan | 10000 | 2025-03-29 | 2025-04-05 | - | 30/04/2025 | 31/05/2025 | 10000
| Actual | [5 empty] | Actual | [5 empty] | Actual
Mantenance of Facilities | Plan | NR/UDS/WACWISA/WK/002/25 | 24000 | NCT | POST | ETC | Plan | 2025-02-19 | 2025-02-24 | 2025-03-10 | 2025-03-17 | 2025-03-24 | Plan | 24000 | 2025-03-31 | 2025-04-07 | - | 30/04/2025 | 31/05/2025 | 24000
| Actual | [5 empty] | Actual | [5 empty] | Actual
Construction of U-drain | Plan | NR/UDS/WACWISA/WK/003/25 | 7400 | PQ | POST | HE | Plan | 2025-02-20 | 2025-02-25 | 2025-03-11 | 2025-03-18 | 2025-04-01 | Plan | 7400 | 2025-04-08 | 2025-04-15 |  | 08/05/2025 | 31/05/2025 | 7400
| Actual | [5 empty] | Actual | [5 empty] | Actual
Plumbing Works at the WACWISA Eatry | Plan | NR/UDS/WACWISA/WK/004/25 | 800 | PQ | POST | HE | Plan | 2025-02-20 | 2025-02-25 | 2025-03-11 | 2025-03-18 | 2025-04-01 | Plan | 800 | 2025-04-08 | 2025-04-15 |  | 08/05/2025 | 31/05/2025 | 800
| Actual | [5 empty] | Actual | [5 empty] | Actual
Installation of Lift | Plan | NR/UDS/WACWISA/WK/002/24 | 115384.6154 | NCT | POST | ETC | Plan | 2024-01-30 | 2024-02-06 | 2024-02-20 | 2024-02-27 | 2024-03-05 | Plan | 115384.6154 | 2024-03-12 | 2024-03-19 | - | 2024-03-26 | 03/04/2024 | 115384.6154
| Actual | NR/UDS/WACWISA/WK/002/24 | 111,528.97 |  |  |  | Actual | 27/05/2024 | 03/06/2024 | 21/06/2024 | 22/06/2024 | 26/06/2024 | Actual | 111,528.97 | 26/06/2024 | 26/06/2024 |  | 21/01/2025
Total Cost | Plan |  | 157584.6154 |  |  |  | Plan | [5 empty] | Plan | 157584.6154 | [5 empty] | 157584.6154
| Actual |  | 111,528.97 |  |  |  | Actual | [5 empty] | Actual | 111,528.97
Formulas:
Tendering Period = [Tender Documents]+5
Tender Closing-Opening = [Tendering Period]+14
Tender Evaluation = [Tender Closing-Opening]+7
Aproval by Final Authority = [Tender Evaluation]+7
Date Contract Award = [Aproval by Final Authority]+7
Date Contract Signature = [Date Contract Award]+7